## Detailed cost plan
PROJECT COST PLAN |  | LAST UPDATED: | 2020-08-31
PROJECT STATUS
|  | ORIGINAL BUDGET | CURRENT PROJECT STATUS |  | PROJECT FORECAST | [6 empty] | UNDER BUDGET
ID | Activity | Budget | Spend to date | Funds remaining | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Funds needed to finish | BUDGET CHECK
1 | Section 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Item 1 |  |  | 0 | [6 empty] | 0 | 0
1.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
1.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
1.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
1.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
2 | Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Item 1 |  |  | 0 | [6 empty] | 0 | 0
2.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
2.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
2.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
2.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
3 | Section 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Item 1 |  |  | 0 | [6 empty] | 0 | 0
3.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
3.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
3.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
3.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
4 | Section 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Item 1 |  |  | 0 | [6 empty] | 0 | 0
4.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
4.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
4.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
4.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
5 | Section 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Item 1 |  |  | 0 | [6 empty] | 0 | 0
5.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
5.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
5.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
5.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
| SUBTOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Total risk allocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Risk 1 |  |  | 0 | [6 empty] | 0 | 0
6.2 | Risk 2 |  |  | 0 | [6 empty] | 0 | 0
6.3 | Risk 3 |  |  | 0 | [6 empty] | 0 | 0
6.4 | Risk 4 |  |  | 0 | [6 empty] | 0 | 0
6.5 | Risk 5 |  |  | 0 | [6 empty] | 0 | 0
7 | Total project contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Overall contingency needed |  |  | 0 | [6 empty] | 0 | 0
7.1 | Contingency Item 1 |  |  | 0 | [6 empty] | 0 | 0
7.2 | Contingency Item 2 |  |  | 0 | [6 empty] | 0 | 0
7.3 | Contingency Item 3 |  |  | 0 | [6 empty] | 0 | 0
7.4 | Contingency Item 4 |  |  | 0 | [6 empty] | 0 | 0
7.5 | Contingency Item 5 |  |  | 0 | [6 empty] | 0 | 0
| TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contingency works slightly differently. Enter a total amount and then draw down again each of the line items accordingly.
Note on C44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert an overall figure, or add more rows to break down your contingency items.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The amount you know or estimate the item will cost at the outset of your project.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The total amount you have spent on each line item so far.
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add more columns as required.

## Cost report
Cost Plan Summary Statement
The project has an overall budget of: | 0
To date, the project has spent: | 0
The project has the following funds remaining (excl. risk & contingency): | 0
In order to complete the project, we need to spend a further: | 0
The project is therefore UNDER BUDGET to the tune of: | 0
The remaining risk and contingency budgets (combined) amount to: | 0
Therefore, the budget remaining if risk and contingency are included is: | 0

## Detailed cost plan (example)
Our Awesome Road Trip! |  | LAST UPDATED: | 2020-08-31
[8 empty] | YOU COULD DELETE THESE COLUMNS |  |  |  | PROJECT STATUS
|  | ORIGINAL BUDGET | CURRENT PROJECT STATUS |  | PROJECT FORECAST | [6 empty] | OVER BUDGET
ID | Activity | Budget | Spend to date | Funds remaining | September | October | November | n/a | n/a | n/a | Funds needed to finish | BUDGET CHECK
1 | Car running costs | 1000 | 200 | 800 | 200 | 200 | 250 | 0 | 0 | 0 | 650 | 150
1.1 | Fuel | 1000 | 200 | 800 | 200 | 200 | 250 |  |  |  | 650 | 150
1.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
1.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
1.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
1.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
2 | Food | 1200 | 448.8 | 751.2 | 465 | 450 | 465 | 0 | 0 | 0 | 1380 | -628.8
2.1 | Meals | 700 | 344.2 | 355.8 | 350 | 345 | 350 |  |  |  | 1045 | -689.2
2.2 | Random snacks | 200 | 21.2 | 178.8 | 30 | 25 | 30 |  |  |  | 85 | 93.8
2.3 | Special occasions/fancy nights out | 300 | 83.4 | 216.6 | 85 | 80 | 85 |  |  |  | 250 | -33.4
2.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
2.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
3 | Accommodation | 3600 | 685 | 2915 | 775 | 750 | 775 | 0 | 0 | 0 | 2300 | 615
3.1 | Overnight stay for two. 120 nights. | 3600 | 685 | 2915 | 775 | 750 | 775 |  |  |  | 2300 | 615
3.2 | Item 2 |  |  | 0 | [6 empty] | 0 | 0
3.3 | Item 3 |  |  | 0 | [6 empty] | 0 | 0
3.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
3.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
4 | Entertainment & sightseeing | 4000 | 1020.6 | 2979.4 | 725 | 800 | 1680 | 0 | 0 | 0 | 3205 | -225.6
4.1 | Bungee jump on final day (£200 each) | 400 | 0 | 400 | 0 | 0 | 400 |  |  |  | 400 | 0
4.2 | Helicopter ride | 800 | 885 | -85 | 0 | 0 | 0 |  |  |  | 0 | -85
4.3 | City tour (with wine tasting) | 100 | 60.6 | 39.4 | 0 | 0 | 0 |  |  |  | 0 | 39.4
4.4 | 3-day camping trip | 500 | 75 | 425 | 350 | [5 empty] | 350 | 75
4.5 | 5* hotel - grand finale! | 200 | 0 | 200 |  |  | 480 |  |  |  | 480 | -280
4.6 | Excursion 1 (to be decided!) | 400 | 0 | 400 | 375 | [5 empty] | 375 | 25
4.7 | Excursion 2 (to be decided!) | 400 | 0 | 400 |  | 400 |  |  |  |  | 400 | 0
4.8 | Excursion 3 (to be decided!) | 400 | 0 | 400 |  | 400 |  |  |  |  | 400 | 0
4.9 | Excursion 4 (to be decided!) | 400 | 0 | 400 |  |  | 400 |  |  |  | 400 | 0
4.1 | Excursion 5 (to be decided!) | 400 | 0 | 400 |  |  | 400 |  |  |  | 400 | 0
5 | Insurances | 233 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Car insurance | 200 | 200 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
5.2 | Personal belongings insurance | 15 | 15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
5.3 | Personal injury/travel insurance | 18 | 18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
5.4 | Item 4 |  |  | 0 | [6 empty] | 0 | 0
5.5 | Item 5 |  |  | 0 | [6 empty] | 0 | 0
| SUBTOTALS | 10033 | 2587.4 | 7445.6 | 2165 | 2200 | 3170 | 0 | 0 | 0 | 7535 | -89.4
6 | Total risk allocation | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
6.1 | Car breakdown callout | 150 | 0 | 150 | 0 | 0 | 0 |  |  |  | 0 | 150
6.2 | Risk 2 |  |  | 0 | [6 empty] | 0 | 0
6.3 | Risk 3 |  |  | 0 | [6 empty] | 0 | 0
6.4 | Risk 4 |  |  | 0 | [6 empty] | 0 | 0
6.5 | Risk 5 |  |  | 0 | [6 empty] | 0 | 0
7 | Total project contingency | 200 | 30 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170
7 | Overall contingency needed | 200 |  | 200 | 0 | 0 | 0 |  |  |  | 0 | 200
7.1 | Extra petrol top-up in August |  | 30 | -30 | 0 | 0 | 0 |  |  |  | 0 | -30
7.2 | Coningency Item 2 |  |  | 0 | [6 empty] | 0 | 0
7.3 | Coningency Item 3 |  |  | 0 | [6 empty] | 0 | 0
7.4 | Coningency Item 4 |  |  | 0 | [6 empty] | 0 | 0
7.5 | Coningency Item 5 |  |  | 0 | [6 empty] | 0 | 0
| TOTALS | 10383 | 2617.4 | 7765.6 | 2165 | 2200 | 3170 | 0 | 0 | 0 | 7535 | 230.6
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contingency works slightly differently. Enter a total amount and then draw down again each of the line items accordingly.
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert an overall figure, or add more rows to break down your contingency items.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The amount you know or estimate the item will cost at the outset of your project.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The total amount you have spent on each line item so far.
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deposit paid
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add more columns as required.

## Cost report (example)
Cost Plan Summary Statement
The project has an overall budget of: | 10383
To date, the project has spent: | 2617.4
The project has the following funds remaining (excl. risk & contingency): | 7445.6
In order to complete the project, we need to spend a further: | 7535
The project is therefore OVER BUDGET to the tune of: | -89.4
The remaining risk and contingency budgets (combined) amount to: | 320
Therefore, the budget remaining if risk and contingency are included is: | 230.6